## Slide 1: Northern Lincolnshire Healthy Lives Healthy Futures Programme
Programme Highlight Report
December

## Slide 2: HLHF Programme Highlight Report
Workstream/Lead | Progress | New Risks/Issues | Next Steps/Key Actions | Date of next meeting
CLINICAL LEADERSHIP Dr Robert Jaggs-Fowler | CLG met 18th June to consider approach to the out of hospital model Agreed to develop models for NL/NEL respectively with pilots operational from October 2015 Considered draft clinical Memorandum of Understanding and draft “Local Operating Framework” for out of hospital models |  | Meetings to be arranged in NL to develop model CLG members to feed back comments on clinical MOU MOU refined following feedback Progress to be shared at next CLG meeting | 14th July
MARKETING, COMMUNICATIONS AND ENGAGEMENT Lisa Hilder | MCE Met 17th June Agreed programme of engagement will start in July Condensed version of the HLHF narrative produced MCE risks considered and updated | Lack of a structured approach/plan to cross organisational workforce engagement and OD could significantly hamper the progress of the clinical/staff engagement process Lack of clear timeframes for delivery of key transformational proposals will hamper effective engagement and consultation, risking judicial review | Develop programme of engagement activities to start in July Assign engagement leads to each HLHF project Update risk register with MCE risks identified Work to strengthen link between clinical engagement and care design process with MCE | 16th July

## Slide 3
Workstream/Lead | Progress | New Risks/Issues | Next Steps/Key Actions | Date of next meeting
MARKETING, COMMUNICATIONS AND ENGAGEMENT Lisa Hilder |  | Lack of timely implementation of agreed schemes could damage stakeholder confidence in deliverability of the programme Lack of local authority participation in the MCE group may mean key messages are not aligned across all organisations If HLHF is not aligned with Comms from surrounding review programmes (i.e Lincolnshire LHAC), this could cause confusion for the public and key stakeholders and damage credibility of plans |  | 
PLANNING AND RESOURCES Caroline Briggs | TOR finalised HLHF model principles document developed Ratification of financial model Draft programme KPIs developed |  | Share and refine draft list of programme KPIs and ensure alignment with HLHF Quality and Outcomes Framework | 1st July

## Slide 4
Workstream/Lead | Progress | New Risks/Issues | Next Steps/Key Actions | Date of next meeting
WORKFORCE AND OD Karen Dunderdale | Draft approach document drafted Date set for PMO to draft workstream timeline with Simon Dunn (29.06.15) Possible workforce and OD lead identified | Timescales associated with recruiting workforce and OD lead could impact on delivery against current timelines | Workforce timeline to be drafted and incorporated into programme plan Appoint workforce and OD lead Establish a baseline of current workforce and skills gap analysis | 23rd July
FINANCE Therese Paskell Laura Whitton Marcus Hassall | Information gathered for risk mapping Finance leads for project confirmed Consideration of future years gap and how to address Need for joint planning process agreed | Lack of identified schemes for 2016/17 | Lock in session (September) to assess financial impact the models being developed by CLG and review impact of schemes not yet assessed via the HLHF model | 8th July
ESTATES Jug Johal | Existing groups to remain and report to PRG Agreement that Jug Johal will be workstream lead and link with NL/NEL leads Mapping work in NL begun NL Workshop 24th July to assess mapping and quick wins re rationalisation of estate across organisations |  | Workshop 24th July (NL) Assessment of quick wins re rationalisation | 24th July (NL)
INFORMATION TECHNOLOGY Pam Clipson (NEL) TBC (NL) | Existing groups to remain and report to PRG Pilot roll out of web V in NL GP practice in progress |  | Confirm NL Lead | 

## Slide 5: Project exceptions against plan
Workstream | Exception against plan | RAG | Action Required | Action Owner | Action Completion date
For example purposes at this stage. This table will be used to highlight any exceptions to the HLHF programme plan currently in development